## Summary
X-Retina FYP-I - Team workplan tracker
Aiman -> Maheen -> Amna ¦ Progress below updates automatically from the Status columns
Section | Total | Not started | In progress | Blocked | Done | % Done
Phase 0 - Setup | 7 | 7 | 0 | 0 | 0 | 0%
Phase 1 - Dependent chain | 4 | 4 | 0 | 0 | 0 | 0%
Phase 1 by owner | Steps assigned | Done | % Done
Aiman | 2 | 0 | 0%
Maheen | 1 | 0 | 0%
Amna | 1 | 0 | 0%
How to use
1. Blue text = cells you edit: Status (dropdown), Date Done (format 08-Oct-2026) and Notes.
2. Black text = formulas or fixed plan content. Do not overwrite.
3. Work top to bottom: Phase 0 first, then Phase 1 steps in order. A step starts only after the previous owner's pull request is merged.
4. Owner colours: Aiman = blue, Maheen = green, Amna = orange, Everyone = grey.
5. Plan assumptions: plain EfficientNet-B4 is the FYP-I baseline; stratified APTOS split; EyePACS subset of about 10-15k images; 380x380 training size. Change them with your supervisor if needed.

## Phase0_Setup
Phase 0 - One-time setup (before any coding)
X-Retina FYP-I ¦ Blue cells are for you to edit (Status, Date Done, Notes)
# | Task | Owner | How | Done when | Status | Date Done | Notes
0.1 | Create the private GitHub repo 'x-retina' | Aiman | Exact commands come with the scaffold | Repo exists with the first commit | Not started
0.2 | Invite teammates as collaborators | Aiman | Repo > Settings > Collaborators | Maheen and Amna both accept | Not started
0.3 | Create shared Drive folder XRetina_Shared/ with subfolders processed/, splits/, checkpoints/, outputs/ | Aiman | Share with both as Editor | Both can see it under 'Shared with me' | Not started
0.4 | Add the Drive folder as a shortcut in My Drive | Everyone | Right-click > Add shortcut to Drive | Folder appears in each person's Colab file panel | Not started
0.5 | Create a Kaggle API token and save it in Colab Secrets (never commit it) | Everyone | Kaggle > Settings > Create New Token | 'kaggle datasets list' works in Colab | Not started
0.6 | Create a GitHub personal access token (repo scope) and save it in Colab Secrets | Everyone | GitHub > Settings > Developer settings | 'git clone' works inside Colab | Not started
0.7 | Run the bootstrap cell (mount Drive, clone repo, install requirements) at the top of every notebook | Everyone | Cell provided in the repo | Same code runs for all three | Not started
Note: 'Everyone' rows (0.4-0.7) must be completed by all three members; track in Notes who is still pending.
Storage warning: free Drive quota is 15 GB. Raw Kaggle downloads stay on Colab's local /content disk, never on Drive. Only processed images, the splits CSV and checkpoints go to the shared Drive, so keep the EyePACS subset small.

## Phase1_Chain
Phase 1 - Dependent chain (who passes to whom)
Due dates follow the FAST NUCES FYP-I Fall 2026 calendar (end of the stated academic week). Blue cells are for you to edit.
Step | Owner | Task | Receives from | Hands off | Calendar week | Due date | Done when | Status | Date Done | Days left | Notes
1 | Aiman | Download APTOS and the EyePACS subset; apply circular crop, CLAHE and resize; build stratified train/val/test split | Phase 0 complete | Processed images in Drive processed/, splits/manifest.csv (path, label, split), merged PR | Week 8 (5-11 Oct) | 2026-10-11 | Notebook runs end to end from a fresh Colab, class counts printed, Maheen confirms she can open the data | Not started |  | 7
2 | Maheen | Build dataloaders and augmentations, training engine (scheduler, early stopping, checkpointing on validation), and metrics (accuracy, QWK, per-class recall, confusion matrix) | Aiman's manifest.csv and processed data | Tested trainer, metrics module and config file, merged to main | Week 9 (12-18 Oct) | 2026-10-18 | Smoke test trains 1-2 epochs on a small subset with no errors | Not started |  | 14
3 | Amna | Train and validate baseline EfficientNet-B4 on APTOS, then on the EyePACS subset; record results | Maheen's trainer, metrics and configs | Checkpoints in Drive checkpoints/, results table, intermediate-results summary | Week 10 (19-25 Oct) | 2026-10-25 | Baseline QWK and accuracy logged - this is the working prototype for the graded Week 10 checkpoint | Not started |  | 21
4 | Aiman | In parallel after Step 1: implement Focal Loss and SMOTE on backbone embeddings; compare against cross-entropy | Maheen's trainer (Step 2) | Losses and imbalance modules in src/, merged | Weeks 9-12 (12 Oct-8 Nov) | 2026-11-08 | Comparison table ready for the mid-term evaluation (6-8 Nov) | Not started |  | 35
Days left = Due date minus today (recalculates automatically; blank once Status is Done; negative means overdue).
Source: due dates are the last day of the calendar weeks in FAST_NUCES_FYP-1_Weekly_Calendar_Fall_2026.pdf. Step 4 spans Weeks 9-12 and ends 8 Nov (end of Week 12, mid-term evaluation window).
Formulas:
Days left = IF([Status]="Done","",[Due date]-TODAY())

## Handoff_Rules
Handoff rules
So nobody waits on, or breaks, anyone else's work
# | Rule | Why
1 | Code travels by GitHub; data and checkpoints travel by Drive - never the other way | The data folder is gitignored, and notebooks stay small and mergeable
2 | Each step ends with a pull request into main; the next person starts only after it is merged | Everyone builds on the same code
3 | The giver posts a short note in the repo (what was done, file paths, anything to watch for) and tags the next person | The receiver does not have to guess
4 | Never edit someone else's step branch. Use your own: aiman/data, maheen/trainer, amna/baseline | Avoids merge conflicts
5 | Start every Colab session with git pull | Everyone sees the latest code